## Sheet1
Ticket No | Date | Time Opened | Opened By | Vendor | Task Detail | Priority | Assigned to | Status | Update | Last Modified
1 | 2026-04-10 | 17:50 | Sanjeev | Project | TUV Required Signed Work Order from our end. | Medium | Swanand Gharpure | Closed By Swanand Gharpure | Reply to his Email has been sent by Swanand and VNR Ma'am | 2026-04-10 00:00:00 17:50:00
2 | 2026-04-10 | 18:13 | Sanjeev | Project | Documents required for registering in SAP for billing | High | Sandeep Ambule | Closed | N/A | 2026-04-10 00:00:00 18:13:00
3 | 2026-04-11 | 14:21 | Sanjeev | Project | Marol F Plot basement water accumulation clearance | High | Sandeep Ambule, Kuldeep (LP), Mahesh (LP), Yuvraj | Closed | N/A | 2026-04-11 00:00:00 14:21:00
4 | 2026-04-11 | 15:55 | Sanjeev | Project | Payment release for Exterior Glass of 16,000 | Medium | Sandeep Ambule, Rizwan | Closed | N/A | 2026-04-11 00:00:00 15:55:00
5 | 2026-04-11 | 18:39 | Sandeep | Admin | Site Serenity Flora tap and area water line broken and leaking | Medium | Vaibhav, Yuvraaj | Closed | N/A | 2026-04-11 00:00:00 18:39:00
6 | 2026-04-13 | 12:40 | Sanjeev | Project | Exterior Glass (Hardeep Singh) Require confirmation to process the payment of 16,000 | Medium | Sandeep Ambule | Closed | N/A | 2026-04-13 00:00:00 12:40:00
7 | 2026-04-13 | 16:05 | Sanjeev | Accounts | Ploomm Request to release balance amount as per our calculation | Medium | Sandeep Ambule | Closed | N/A | 2026-04-13 00:00:00 16:05:00
8 | 2026-04-16 | 15:30 | Sanjeev | Accounts | TUV Request approval for generating tax invoice for Feb & March | High | Sandeep Ambule & Swanand Gharpure | Closed | N/A | 2026-04-16 00:00:00 15:30:00
9 | 2026-04-19 | 19:30 | Sanjeev | Legal | Anwin Buildcon Stamp paper and Exit pass email reply | High | Swanand Gharpure | Closed | N/A | 2026-04-19 00:00:00 19:30:00
10 | 2026-04-20 | 16:42 | Sanjeev | Projects & Accounts | Bharat Interior HIEX rooms certification and payment release | High | Sandeep Ambule & Rizwan Sir | Closed By Sandeep Ambule | N/A | 2026-04-20 00:00:00 16:42:00
11 | 2026-04-21 | 17:17 | Swanand | Accounts & Legal | Accounts and paperwork closure of Whiterock | Medium | Sandeep Ambule & Swanand Gharpure | Open | The partial Work Allocation Letter has been executed on 24.04.2026 for an amount of Rs. 5,34,717 (including GST). We require inputs from the Project Team for discussion with the vendor and finalisation of the rate per square foot for the CC Building canopy saga soffit panel, Mangalore tile ceiling, and Sky Lift side – Mangalore tile ceiling. | 2026-04-21 00:00:00 17:17:00
12 | 2026-04-21 | 19:46 | Sandeep | Accounts | PT Work | High | Dimple & Yashwant | Closed By Dimple | duplicate of Ticket No. 35. Partial updates have been migrated to the primary ticket. Please refer to the active ticket for further progress. | 2026-04-21 00:00:00 19:46:00
13 | 2026-04-21 | 19:47 | Sandeep | Accounts | COMPLIANCE, PF & ESIC Working | High | Dimple & Yeshwant Kahar | Open |  | 2026-04-21 00:00:00 19:47:00
14 | 2026-04-21 | 19:48 | Sandeep | Admin | Car BMW Altis | High | Vaibhav & Nisha | Open – Partial done | N/A | 2026-04-21 00:00:00 19:48:00
15 | 2026-04-21 | 19:50 | Sandeep | Accounts | Jio Bill payment - +912235099150 | High | Yeshwant Kahar | Open |  | 2026-04-21 00:00:00 19:50:00
16 | 2026-04-21 | 19:51 | Sandeep | Accounts | Gst Tracker | Medium | Dimple | Closed By Dimple Patil | N/A | 2026-04-21 00:00:00 19:51:00
17 | 2026-04-21 | 19:53 | Sandeep | Accounts | TDS sheet Group | Medium | Dimple | Closed By Dimple Patil | N/A | 2026-04-21 00:00:00 19:53:00
18 | 2026-04-21 | 15:00 | Sandeep | Accounts | Group Bank Balance | Medium | Dimple | Closed By Dimple Patil | N/A | 2026-04-21 00:00:00 15:00:00
19 | 2026-04-21 | 15:00 | Sandeep | Accounts | Cheque Clearance | Medium | Yeshwant Kahar | Closed |  | 2026-04-21 00:00:00 15:00:00
20 | 2026-04-21 | 19:48 | Management | Admin | Car BMW | High | Sandeep Ambule | Open – Partial done | N/A | 2026-04-21 00:00:00 19:48:00
21 | 2026-04-22 | 10:12 | Sandeep | IT | Tally software renewal and get quotation | High | Sanjeev | Open | Quotation received from vendor and cheque for the same ammount sent for signature to close this | 2026-05-05 12:44:08
22 | 2026-04-22 | 10:41 | Sandeep | IT | Winman software payment and TDS Renewal | High | Sanjeev | Open | Proforma Invoice Received and asked accounts team to prepare cheque for the amount: 11,460 | 2026-04-22 00:00:00 10:41:00
23 | 2026-04-22 | 10:50 | Sanjeev | Accounts | TUV@ Tax invoice month of Feb'26 and Mar'26_K Raheja | Medium | Yeshwant Kahar & Sandeep Ambule | Closed | N/A | 2026-04-22 00:00:00 10:50:00
23 | 2026-04-22 | 10:51 | Sandeep | Accounts | HDFC 1802 SPHPL KYC | Medium | Yeshwant Kahar | Closed By Yeshwant | N/A | 2026-04-22 00:00:00 10:51:00
24 | 2026-04-22 | 10:53 | Dimple | Accounts | ESIC payment updates | High | Dimple | Closed By Dimple Patil | Payment done for Feb 2026 and March 2026 | 2026-04-22 00:00:00 10:53:00
25 | 2026-04-22 | 10:55 | Dimple | Accounts | Fund transfer from Kotak 050 | High | Dimple & Sandeep Ambule | Closed By Dimple Patil | Cheques deposited in bank | 2026-04-22 00:00:00 10:55:00
26 | 2026-04-22 | 12:17 | Sanjeev | Projects & Accounts | Rizwan Sir will put email to accounts to clear balance payment of Evah Construction | High | Yeshwant Kahar | Open | Cheque has been prepared and sent to RH for Signature | 2026-04-22 00:00:00 12:17:00
27 | 2026-04-22 | 13:57 | Dimple | Accounts | Train Yashwant and prepare Accounts SOP list | High | Dimple & Yeshwant Kahar | Closed By Yeshwant | up to 7 PM | 2026-04-22 00:00:00 13:57:00
28 | 2026-04-22 | 14:00 | Swanand |  | Reply on email received from Anwin Buildcon - Mr. Abhinav | High | Swanand Gharpure | Closed | Reply to Anwin Buildcon Pvt. Ltd email has been sent by Swanand Sir | 2026-04-22 00:00:00 14:00:00
29 | 2026-04-22 | 14:08 | Sandeep | Accounts | Train Nisha and prepare Accounts & Admin SOP list | High | Dimple & Nisha | Closed By Sandeep Ambule | up to 7 PM | 2026-04-22 00:00:00 14:08:00
30 | 2026-04-22 | 15:47 | Sandeep | Admin | Office parcel at RH ₹3150 (Paid from Bison to Sanjeev; GPay by Sanjeev) | High | Dimple | Closed By Sandeep Ambule | N/A | 2026-04-22 00:00:00 15:47:00
31 | 2026-04-22 | 16:20 | Dimple |  | Dimple send the Group Compliance Last register now updated with these ESIC Payments updated as on date (Body of email + Excel) | High | Dimple | Closed By Dimple Patil | N/A | 2026-04-22 00:00:00 16:20:00
32 | 2026-04-24 | 10:30 | Dimple | Accounts & Legal | Tax tracker to update by Dimple , Swanand with Divyesh Sir on Saturday 2.30PM | Medium | Dimple and Swanand Gharpure | Closed | N/A | 2026-04-24 00:00:00 10:30:00
33 | 2026-04-27 | 10:20 | Swanand | Accounts & Legal | To share an update on CS Compliance by EOD. | Medium | Dimple and Swanand Gharpure | Open |  | 2026-04-27 00:00:00 10:20:00
34 | 2026-04-27 | 14:13 | Dimple | Accounts | Close GST filing for March 2026 | High | Dimple | Closed By Dimple Patil | N/A | 2026-04-27 00:00:00 14:13:00
35 | 2026-04-27 | 14:15 | Dimple | Accounts | To closed PT Compliance by EOD | Medium | Dimple | Open | Status of PT for Dimple Enterprises. Currently, we have filed PT returns for FY 2023-2024 and FY 2024-2025. While reviewing the website, we observed that the filings for FY 2021–22 and FY 2022–23 are not being reflected. We contacted the PT Office; however, they were unable to provide clarity on the issue. Additionally, while reviewing the website, we observed that the filings for FY 2021–22 and FY 2022–23 are not being reflected. We contacted the PT Helpdesk; however, they were unable to provide clarity on the issue. We will recheck the website, and if the issue persists, we will visit the PT Office for further clarification. | 2026-04-27 00:00:00 14:15:00
36 | 2026-04-27 | 14:17 | Sandeep | Admin | car Management sheet format updates by 4.30 PM | Medium | Yuvraj, Vaibhav & Sanjeev | Open | N/A | 2026-04-27 00:00:00 14:17:00
37 | 2026-04-27 | 14:31 | Sanjeev | Accounts | Elson PR - ESSC Tax Invoice for Retainer Fees ¦ April - May 2026 | Medium | Yeshwant Kahar | Open | N/A | 2026-04-27 00:00:00 14:31:00
38 | 2026-04-27 | 21:31 | Sanjeev | Projects & Accounts | Aryama Signage Vendor following up for payment as they have only got approx 20% payment. | Medium | Yeshwant Kahar | Open | Yeshwant to prepare cheque as per WAL payment schedule till 80% of tax invoice | 2026-04-27 00:00:00 21:31:00
39 | 2026-04-28 | 12:40 | Sanjeev | Legal | Swanand to close paperwork for VERGO ACP material warranty | Medium | Swanand Gharpure | Open | N/A | 2026-04-28 00:00:00 12:40:00
40 | 2026-04-28 | 13:00 | Sandeep | Accounts | Kotak Zurik Sunlight - Swanand - Reply mail require to share May 26 insurance quotation month quarterly | Medium | Sandeep Ambule | Open | Advise required from management | 2026-04-28 00:00:00 13:00:00
41 | 2026-04-28 | 13:23 | Sandeep | Accounts | Reco with bank statement vs master tracker to check any utility is pending | Medium | Yeshwant Kahar and Nisha | Closed By Sandeep Sir |  | 2026-04-28 00:00:00 13:23:00
42 | 2026-04-29 | 22:16 | Dimple | Accounts | Group Compliance Status - Excel and in Body of Mail | High | Dimple | Closed By Dimple Patil | N/A | 2026-04-29 00:00:00 22:16:00
44 | 2026-04-29 | 20:30 | Sandeep | Accounts | Car loan Rs.900 to solve on urgent basis | High | Sandeep Ambule | Closed By Sandeep Ambule |  | 2026-04-29 00:00:00 20:30:00
45 | 2026-04-29 | 22:08 | Sanjeev | Legal | Unauthorized construction adjacent to our Ramada Service Gate boundary wall | High | Vyas & Swanand Gharpure | Open | The Legal Team will be filing an official complaint with the BMC on Monday. | 2026-04-29 00:00:00 22:08:00
46 | 2026-04-29 | 22:08 | Sanjeev | Legal | Close paper work of Siemens | High | Swanand Gharpure | Closed By Swanand Gharpure | N/A | 2026-04-29 00:00:00 22:08:00
47 | 2026-04-29 | 22:08 | Sanjeev | Legal | Close paper work of Compress India | High | Swanand Gharpure | Closed By Swanand Gharpure | N/A | 2026-04-29 00:00:00 22:08:00
48 | 2026-04-30 | 11:47 | Sandeep | Admin | car paper work of : BMW, JAGUAR, CIAZ, ALTIS, DEZIRE | High | Vaibhav | Open | Respected Sir Please note that Ajit mobile is switch off... I will go to Andheri RTO to meet Ajit if call Will not received.. Further May I send Yuvraj to get documents from RH which was sent for KLR sir for Dzire and ciaz car | 2026-04-30 00:00:00 11:47:00
49 | 2026-04-30 | 12:08 | Sandeep | Accounts | SPHPL AMEX KYC | Medium | Nisha | Open |  | 2026-04-30 00:00:00 12:08:00
50 | 2026-04-30 | 12:09 | Sandeep | Accounts | NKR sir DBS bank KYC form filling | Medium | Yeshwant Kahar | Open | N/A | 2026-04-30 00:00:00 12:09:00
51 | 2026-04-30 | 12:10 | Sandeep | Accounts | Draft DE E invoice May 2026 | Medium | Sandeep Ambule | Closed By Sandeep Ambule | N/A | 2026-04-30 00:00:00 12:10:00
52 | 2026-04-30 | 12:10 | Sandeep | Accounts | Chq image send to Swanad Sunlight Ramada Kotak account | Medium | Sandeep Ambule | Open | N/A | 2026-04-30 00:00:00 12:10:00
53 | 2026-04-30 | 12:49 | Sanjeev | Legal | Vaibhav and Vyas will close pending items related to hotel BMC water, and Mahanagar Gas. | Medium | Vyas & Vaibhav | Open | N/A | 2026-04-30 00:00:00 12:49:00
54 | 2026-04-30 | 12:52 | Dimple | Accounts | GSTR 9 & 9C for FY 24-25 | High | Sandeep Ambule and Dimple | Open | N/A | 2026-04-30 00:00:00 12:52:00
55 | 2026-04-30 | 13:00 | Sanjeev | Accounts | Sunny Nursary - Accounts team to release balance payment after management approval | Medium | Yeshwant Kahar | Open | N/A | 2026-04-30 00:00:00 13:00:00
56 | 2026-04-30 | 14:08 | Dimple | Accounts | Share sealed envelope of Group Bank and FD Balances | Medium | Dimple and Nisha | Closed By Dimple Patil | N/A | 2026-04-30 00:00:00 14:08:00
57 | 2026-04-30 | 14:08 | Dimple | Accounts | Group Compliances - Email + Print | Medium | Dimple & Sandeep Ambule | Closed By Dimple Patil | N/A | 2026-04-30 00:00:00 14:08:00
58 | 2026-04-30 | 14:10 | Dimple | Accounts | SHARE CHEQUE BOOKS IN HO LIST ACCOUNT WISE | Medium | Sandeep Ambule & Yeshwant Kahar | Closed By Yeshwant |  | 2026-04-30 00:00:00 14:10:00
59 | 2026-04-30 | 14:10 | Dimple | Accounts | Credit Cards Updated Tracker with complete Reconciliation | Medium | Yeshwant Kahar & Nisha & Dimple | Closed By Dimple Patil | N/A | 2026-04-30 00:00:00 14:10:00
60 | 2026-04-30 | 14:10 | Swanand | Legal | Draft Reply to Ambika Waters | High | Aditi & Swanand Gharpure | Closed By Swanand Gharpure | N/A | 2026-04-30 00:00:00 14:10:00
61 | 2026-04-30 | 14:12 | Dimple | Accounts | Project Expense Tracker updated as on date. (Email+Print) | Medium | Yeshwant Kahar & Dimple | Closed By Dimple | The mail has been shared with proper reconciliation. | 2026-04-30 00:00:00 14:12:00
62 | 2026-04-30 | 14:12 | Swanand | Legal | Discuss way forward with Pushkar Sir | High | Vyas & Swanand Gharpure | Closed By Swanand Gharpure | N/A | 2026-04-30 00:00:00 14:12:00
63 | 2026-04-30 | 14:15 | Dimple | Accounts | GST and TDS review for FY 2025-26 Month wise | Medium | Yeshwant Kahar, Dimple & Nisha | Closed By Dimple | stands closed as the mail has been shared on Saturday. | 2026-04-30 00:00:00 14:15:00
64 | 2026-04-30 | 14:17 | Dimple | Accounts | Updated Group Tax Tracker (Saturday @ 12.30 PM) | Medium | Sandeep Ambule and Dimple | Closed By Dimple | Updated Group tax tracker has been shared on Mail. | 2026-04-30 00:00:00 14:17:00
65 | 2026-04-30 | 14:21 | Dimple | Accounts | SPHPL - notice for RCM payable (ASMT-10) | Medium | Sandeep Ambule and Dimple | Open | N/A | 2026-04-30 00:00:00 14:21:00
66 | 2026-04-30 | 14:25 | Swanand | Legal | To speak with Abhishek Sir and Harsh Sir on legal matters | Medium | Vyas & Swanand Gharpure | Closed By Swanand Gharpure | N/A | 2026-04-30 00:00:00 14:25:00
67 | 2026-04-30 | 19:11 | Swanand | Legal | To follow up with HN Legal regarding the draft application for status quo and to finalise the same in the Sameer Khan matter | High | Swanand Gharpure | Open | N/A | 2026-04-30 00:00:00 19:11:00
68 | 2026-05-02 | 14:21 | Sandeep | Accounts | Zurich And Sunlight - follow up Department Ramada insurance policy | High | Sandeep Ambule | Closed By Sandeep Ambule | N/A | 2026-05-02 00:00:00 14:21:00
69 | 2026-05-02 | 14:21 | Sandeep | Accounts | Zurich And Sunlight - follow up Ramada insurance policy Apr 2026 Refund | High | Sandeep Ambule | Closed By Sandeep Ambule | N/A | 2026-05-02 00:00:00 14:21:00
70 | 2026-05-02 | 19:36:03 | Sandeep | Legal | Unauthorized construction adjacent to our Ramada Service Gate boundary wall | High | Vyas & Swanand Gharpure | Open | N/A | 2026-05-02 19:36:03
71 | 2026-05-04 | 10:56:13 | Sanjeev | Accounts | Meeting with Mishra ( United Guard ) regarding guards salary increment this week. | High | Sandeep Ambule & Sanjeev | Open | N/A | 2026-05-04 10:56:13
72 | 2026-05-04 | 10:57:59 | Sandeep | Accounts | HDFC CC not working will discuss and solve by sending Mail and Task to be closed before today 10:45 AM | High | Sandeep Ambule | Closed By Sandeep Sir | Request to NKR sir, Please approve HDFC cr card mail for updating promo code | 2026-05-04 10:57:59
73 | 2026-05-04 | 10:59:36 | Sandeep | Accounts | Zurich and Unilight - Insurance policy Ramada Apr 26 and task to be close on high priority before today 2:30 PM | High | Sandeep Ambule | Closed By Sandeep Sir | Policy shared Full apr 26 month | 2026-05-04 10:59:36
74 | 2026-05-04 | 12:06:01 | Sanjeev | IT | Provide an update on pending works, next steps at the group level within the next 2 hours. Also, include yesterday's group-level security reports. | High | Sanjeev | Closed | Email sent to VNR Ma'am | 2026-05-04 12:06:01
75 | 2026-05-05 | 13:58:58 | Sanjeev | Accounts | Provide a comprehensive recap of all tasks from the past two weeks. Include detailed updates on submissions completed, envelope numbers, pending items, and those that have been checked and signed off. | High | Dimple | Closed By Dimple | The mail has been shared with detailed updates of each task dt 05.05.2026 | 2026-05-05 17:55:56
76 | 2026-05-05 | 14:32:50 | Sanjeev | Accounts | Update on Bluesea cheque, When will it be processed? It's still in head office accounts dept. | High | Yeshwant Kahar | Open |  | 2026-05-05 14:32:50